## Finance
Year Round Responsibilities
Approval Of Unit Money Earning Projects | Ongoing
Fundraising Performance: Achieve district finance goals as defined by our Council. | June
Fundraising Volunteers. Ensure enough volunteers are recruited to achieve fundraising goals. | Ongoing
Oversee District Budgets and present financials at Monthly District Committee Meeting | Ongoing
Assist Units in establishing an annual funding plan that allows every Scout to participate independent of their circumstances | Ongoing
Assist Units in developing a business-like management of their funds to ensure good fiscal responsibly. | Ongoing
Donor Recognition and year-round engagement | Ongoing
New Donor Development / Sub-Committee that introduces individuals to Scouting | Ongoing
Endowment / Sub-Committee grows our Council Endowment | Ongoing
Where applicable, maintain and foster a strong relationship with the United Way and United Givers Fund | Ongoing
FOS Community | 2023-05-05 | WEEKS
BEFORE
Community FOS Chair recruited | 2022-12-02 | -22
Vice Chairs recruited | 2022-12-30 | -18
Table Hosts and Workers recruited | 2023-01-20 | -15
Date, Location, Food and Program set | 2023-01-20 | -15
Table Host / Worker training and kickoff Conducted (With Contributions Received) | 2023-02-10 | -12
Vice Chairs have worked with Table Hosts to fill tables, work past givers and collect contributions | 2023-04-28 | -1
All past givers have been invited to event or worked prior to event | 2023-04-28 | -1
All attended are re-contacted within 24 hours of envent to ensure attendance | 2023-05-05 16:48 | 0.1
Community FOS Event / Luncheon(s) | 2023-05-05 | 0
Luncheon Call down completed (to those who said they would be there and didn't make it) | 2023-05-08 12:00 | 0.5
All Unworked Past Givers Contacted and worked in scoutnet | 2023-05-08 12:00 | 0.5
Community Campaign Goal Reached | 2023-05-12 | 1
Victory Celebration - All FOS Workers thanked | 2023-05-26 | 3
FOS Family | 2023-05-31 | WEEKS
BEFORE
Family FOS Chair Recruited | 2022-10-26 | -31
Presenter Training Date, Time, & Location set | 2022-11-16 | -28
All Presenters and Workers recruited | 2022-12-07 | -25
All Presenters trained | 2022-12-14 | -24
All Unit Presentation Dates Set (Courts of Honor / Blue and Golds) | 2023-01-04 | -21
All Pack Presentations conducted | 2023-03-01 | -13
All Cub Scout Families contacted who were missed during the presentation | 2023-03-15 | -11
All Troop and Crew presentations conducted | 2023-05-24 | -1
All Boy Scout and Venturing Families contacted who were missed during the presentation | 2023-05-27 12:00 | -0.5
All clean up Calldowns Complete and 100% of past givers worked | 2023-05-31 | 0
FOS Family target completion date | 2023-05-31 | 0
Victory Celebration - All Family FOS Workers thanked | 2023-06-21 | 3
FOS Leadership Campaign | 2023-01-31 | WEEKS
BEFORE
Chair Reqruited - (Normally District Chair) | 2022-11-15 | -11
Presentation made at District Committee meeting & Commissioner meeting | 2023-01-10 | -3
Personal calls made to unworked past givers and prospects | 2023-01-24 | -1
All District Volunteers and Merit Badge Counselors are worked | 2023-01-31 | 0
Popcorn | 2023-11-18 | WEEKS
BEFORE
Popcorn Kernel recruited | 2023-03-11 | -36
Contact and Thank past selling Units | 2023-04-22 | -30
Contact units that haven't sold in the past and encourage them to participate | 2023-05-27 | -25
Popcorn Sale Plan & Kick-offs distributed & Promoted (May Program Planning Kick-off) | 2023-05-20 | -26
Popcorn Distribution Location set | 2023-05-20 | -26
Identify and secure quality locations for Storefront sales | 2023-07-01 | -20
Popcorn Orientation & Kick-off | 2023-07-29 | -16
All Unit Online Commitments received & Unit Budgets received | 2023-07-29 | -16
Unit Popcorn Orders submitted | 2023-08-05 | -15
Product Distribution & Popcorn Sale Begins | 2023-08-19 | -13
Additional product orders and left over product returned | 2023-10-07 | -6
Popcorn Sale Ends | 2023-11-18 | 0
Final Payments due | 2023-11-21 12:00 | 0.5
Prize orders submitted | 2023-11-21 12:00 | 0.5
All Outstanding Balances collected | 2023-11-25 | 1
Contact and Thank unit leaders for participating in the sale | 2023-12-02 | 2
Camp Cards | 2015-02-01 | WEEKS
BEFORE
Camp Card Chair Recruited | 2014-11-09 | -12
Camp Card Plan Distributed & Promoted | 2014-11-23 | -10
Unit Camp Card Orders Received | 2014-12-14 | -7
Camp Card Orientation, Kick Off and Supplies delivered | 2015-02-01 | 0
Camp Card Sales Begin | 2015-02-01 | 0
Camp Card money and left over cards turned in | 2015-04-12 | 10
All Outstanding Balances cleaned up | 2015-04-19 | 11
Other | 2023-01-01 | WEEKS
BEFORE
| 2022-12-25 | -1
| 2022-12-25 | -1
| 2022-12-25 | -1
| 2023-01-01 | 0
| 2023-01-08 | 1
| 2023-01-08 | 1

## Membership
Year Round Responsibilities
Market Share: Increase market share | Year End
Membership/Youth Growth: Increase number of registered youth. | Year End
Opportunity to Join: Increase number of new cub scouts | Year End
Youth Retention: Improve retention rate of traditional members. | Year End
New Unit Organization: Start new units | Ongoing
Home School: Maintain relationships and encorage scouting partnerships | Ongoing
Beascout.org: ensure units keep their Beascout pins updated | Ongoing
Fall Recruitment (Cub Scouts) | 2023-09-30 | WEEKS
BEFORE
Cub Scout Recruitment Chair Recruited | 2023-05-13 | -20
District Facilitators / Committee Recruited | 2023-05-27 | -18
Dates set for Fall Recruitment Training(s), calander organized and schools assigned | 2023-06-10 | -16
All Unit New Member Coordinators identified, recruited, and secured | 2023-07-15 | -11
Flyer ordered, All Principles contacted, Sign-up Nights and Scout Talks Dates Set | 2023-07-22 | -10
District Facilitator Training Held | 2023-07-29 | -9
Fall Recruitment Training for Unit Leaders Held - Flyers/ Stickers / promotion items received by Units | 2023-08-05 | -8
Begin Publicity (Flyers, postcards, peer2peer, uniform day, Newspaper, e-mail, facebook, website etc.) | 2023-08-12 | -7
Begin Sign-up Nights | 2023-08-12 | -7
All Sign-up Nights Held - Membership is Reported & Turned In | 2023-09-30 | 0
Schools that need 2nd rallies identifired | 2023-09-30 | 0
All 2nd Rallied Complete | 2023-10-28 | 4
We build Campaigns organized to help units in need of membership growth | 2023-10-28 | 4
Thank You letters, gifts, visits to Principles and volunteers | 2023-11-11 | 6
Spring Recruitment Events - Cubs | 2023-05-15 | WEEKS
BEFORE
Cub Scout Recruitment Chair Recruited | 2023-02-06 | -14
District Facilitators / Committee Recruited | 2023-02-20 | -12
Units with a strong summer program identified | 2023-02-20 | -12
Units with a strong summer program asked to participate | 2023-03-13 | -9
Flyer ordered, All Principles contacted, Sign-up Nights and Scout Talks Dates Set | 2023-03-27 | -7
Unit Leaders, District Facilitators, New Member Coordinators trained as needed | 2023-04-03 | -6
Begin Publicity (Flyers, postcards, peer2peer, uniform day, Newspaper, e-mail, facebook, website etc.) | 2023-04-10 | -5
Begin Sign-up Nights | 2023-04-17 | -4
All Sign-up Nights Held - Membership is Reported & Turned In | 2023-05-15 | 0
Thank You letters, gifts, visits to Principles and volunteers | 2023-06-05 | 3
Arrow of Light to Scout Transition | 2023-05-01 | WEEKS
BEFORE
Arrow of Light to Scout Transition Chair & Committee Recruited | 2023-01-02 | -17
Ensure each Pack has a Den Chief who is trained | 2023-01-16 | -15
Ensure Troops are in contact with AOL Dens and inviting them to attend Troop meetings | 2023-02-06 | -12
Youth Separated List ran | 2023-04-03 | -4
All Scouts from Youth Seperated List Contacted to verify cross over or reason for not crossing over | 2023-05-01 | 0
All applications for cross overs are in office | 2023-05-15 | 2
Fall Recruitment Events (Scouts BSA & Venturing) | 2023-10-31 | WEEKS
BEFORE
Scouts BSA and Venturing Recruitment Chairs Recruited | 2023-07-18 | -15
Recruitment Plan created and shared with Units | 2023-08-29 | -9
Unit Recruitment Dates and activities planned and promotional items ordered | 2023-09-05 | -8
Troops & Crews hold an activity based recruitment event - Membership Reported & Turned In | 2023-10-31 | 0
Volunteers recognized for their efforts | 2023-11-14 | 2
Exploring 1st Nighters | 2023-10-31 | WEEKS
BEFORE
Exploring Recruitment Chairs Recruited | 2023-06-27 | -18
Career Interest Survey's given to Middle and High School Students via Guidance Counselors | 2023-08-22 | -10
Date set for Exploring 1st Nighter Leader Training | 2023-09-12 | -7
All Exploring Post Advisors personally contacted and invited to attend the training | 2023-09-12 | -7
Exploring 1st Nighter Training Held | 2023-09-26 | -5
Using data from the Career Interest Survey's, e-mail invitations are sent to Students to attend 1st Nighter | 2023-10-10 | -3
Additional promotion for each 1st Nighter | 2023-10-10 | -3
Posts hold 1st Nighter Event - Membership Reported & Turned In | 2023-10-31 | 0
Youth who couldn't attend are invited to the next meeting | 2023-11-07 | 1
Volunteers recognized for their efforts | 2023-11-14 | 2

## Activities
Year Round Responsibilities
Increase the percentage of Cub Scouts attending day camp, Cub Summer Camp, and Webelos Resident Camp | July
Promotes and ensures high attendance at Cub Scout Events such as Cub Haunted and Cub Adventure weekend | Ongoing
Encourages unit participation in community service projects | Ongoing
Ensures that service hours are beingn properly recorded in Internet Advancement 2.0 | Ongoing
Promotes the National Summertime Pack Award | Ongoing
Promotes and Encourages attendance at District and Council Events | Ongoing
District Pinewood Derby | 2014-02-28 | WEEKS
BEFORE
Chairman Recruited | 2013-11-08 | -16
Committee Recruited | 2013-11-15 | -15
Planning Meeting to set program, budget, staff, location, and promotion plan | 2013-12-20 | -10
Secure location, permits, sanitation and water | 2013-12-27 | -9
Promotion begins - unit presentations, mailers, e-mail, facebook, website, newsletter | 2014-01-10 | -7
Committee Meeting - Finalize activities & activity rules, maps, recognition etc. | 2014-01-24 | -5
Order program supplies, patches, Ribbons, etc. | 2014-01-24 | -5
Printing - Activity badge cards, Final Instructions etc. | 2014-02-14 | -2
Recheck all preparations, equipment, gather materials, and program gather materials | 2014-02-21 | -1
Event Date | 2014-02-28 | 0
Review meeting/ finalize budget/ Mail thank-yous | 2014-03-07 | 1
Scouting For Food | 2023-11-11 | WEEKS
BEFORE
Chairman Selected | 2023-08-12 | -13
Planning and Promotion meeting | 2023-08-26 | -11
Promotion begins - roundtable, e-mail, facebook, website | 2023-09-09 | -9
Unit calls about participating | 2023-09-23 | -7
Door Hangers Ordered | 2023-10-07 | -5
Door Hangers Pick up | 2023-10-28 | -2
Door Hanger Distribution | 2023-11-04 | -1
Scouting for food pickup | 2023-11-11 | 0
Ensure all collection total are reported | 2023-11-18 | 1
Thank you to unit leaders and volunteers | 2023-11-25 | 2
District-Wide Community Service Project | 2023-06-01 | WEEKS
BEFORE
| 2023-01-26 | -18
| 2023-02-02 | -17
| 2023-02-16 | -15
| 2023-02-16 | -15
| 2023-04-06 | -8
| 2023-04-06 | -8
| 2023-04-06 | -8
| 2023-05-11 | -3
| 2023-05-11 | -3
| 2023-05-18 | -2
| 2023-05-25 | -1
Date of Service Project | 2023-06-01 | 0
| 2023-06-08 | 1
Other Event | 2023-01-01 | WEEKS
BEFORE
| 2022-09-11 | -16
| 2022-09-18 | -15
| 2022-10-23 | -10
| 2022-10-30 | -9
| 2022-11-27 | -5
| 2022-11-27 | -5
| 2022-12-18 | -2
| 2022-12-25 | -1
Event Date | 2023-01-01 | 0
| 2023-01-08 | 1

## Camping
Year Round Responsibilities
Scouts BSA Summer Camp: Increase the number of Scouts attending long-term camp and high-adventure programs | August
Promotes the National Camping Award | Ongoing
Order of the Arrow: Ensure OA is properly functioning in the District | Ongoing
Promotes Scouts BSA Summer Camp Attendance and works toward high attendance | Ongoing
Works with Commissioners to understand and support each unit's year-round camping and outdoor plan | Ongoing
Ensures a Short-Term Camp Administrator inspects and approves all Short-Term camps | Ongoing
Ensures that a Medical Officers is on site at all Short-Term Camps | Ongoing
Quartermaster: Inventories and manages supplies purchase for District events | Ongoing
Scouts BSA Summer Camp Promotion | 2023-05-29 | WEEKS
BEFORE
| 2022-11-28 | -26
| 2022-12-05 | -25
| 2023-01-09 | -20
| 2023-01-23 | -18
| 2023-02-27 | -13
| 2023-03-06 | -12
| 2023-05-15 | -2
| 2023-05-22 | -1
1st Day of Summer Camp | 2023-06-05 | 0
| 2023-06-05 | 1
Camporee | 2017-05-15 | WEEKS
BEFORE
Chairman Recruited | 2016-11-14 | -26
Committee Recruited | 2016-11-21 | -25
Committee Meeting: set program, location, budget, menu, promotion assignments | 2016-12-26 | -20
Secure location, permits, sanitation and water | 2017-01-09 | -18
Committee Meeting - maps, events, recog, patch design, campfire, judges, first aid, signs, hospital, food | 2017-02-13 | -13
Promotion - District meetings, facebook, letters, phone calls, website, e-mail | 2017-02-20 | -12
Promotion - Order of the Arrow Elections | 2017-02-20 | -12
Order program supplies, patches, ribbons, etc. | 2017-03-20 | -8
Printing - Judging Sheets, Final Instructions | 2017-05-01 | -2
Staff meeting - full staff training & Final check of all arrangements | 2017-05-01 | -2
Recheck all preparations, equipment, and program | 2017-05-08 | -1
Camporee | 2017-05-15 | 0
Review meeting / finalize budget / Thank you's sent | 2017-05-22 | 1
Other Event | 2023-01-01 | WEEKS
BEFORE
| 2022-07-03 | -26
| 2022-07-10 | -25
| 2022-08-14 | -20
| 2022-08-28 | -18
| 2022-10-02 | -13
| 2022-10-09 | -12
| 2022-10-09 | -12
| 2022-11-06 | -8
| 2022-12-18 | -2
| 2022-12-18 | -2
| 2022-12-25 | -1
| 2023-01-01 | 0
| 2023-01-08 | 1

## Advancement
Year Round Responsibilities
Cub Scout Advancement: Increase the percentage of Cub Scouts earning rank advancements. | Year End
Scouts BSA Advancement: Increase the percentage of Scouts earning rank advancements | Year End
Promotes Unit Leader Training Awards - (Knots) | Ongoing
Eagle Project Approvals and Eagle Board of Reviews | Ongoing
Recruit and Register Merit Badge Counselors | Ongoing
Ensures leaders have regular access to the Merit Badge Counselor lists | Ongoing
Promote, support, and assist units with Scoutbook and Internet Advancement 2.0 | Ongoing
District Banquet | 2023-04-25 | WEEKS
BEFORE
2023-04-25
2023-04-25
2023-04-25
2023-04-25
2023-04-25
2023-04-25
2023-04-25
2023-04-25
2023-04-25
2023-04-25
2023-04-25
| 2023-04-18 | -1
District Banquet | 2023-04-25 | 0
| 2023-05-02 | 1
Council Adult Leader Awards | 2023-09-30 | WEEKS
BEFORE
Identify individuals to nominate for Council Leader Awards: Silver Beaver, Witney M. Young etc | 2023-07-15 | -11
fill out nomination forms for nominated individuals | 2023-07-22 | -10
Council Adult Leader Award - Turned in to Council Office | 2023-09-30 | 0
follow up: Verify which individuals were selected. Save information on those not selected for next year | 2023-12-09 | 10
Merit Badge Day | 2023-01-01 | WEEKS
BEFORE
Chairman Recruited | 2022-09-18 | -15
Committee Recruited | 2022-09-25 | -14
Committee Meeting: reserve location,, decide on merit badges | 2022-10-09 | -12
Committee Meeting: Set up online registration | 2022-10-09 | -12
Promotion - District meetings, Newsletter, E-blasts, facebook, letters, phone calls, website, e-mail | 2022-10-16 | -11
Committee Meeting: recruit MB counselors for event | 2022-11-06 | -8
Recheck all preparations | 2022-12-25 | -1
Merit Badge Day | 2023-01-01 | 0
Review meeting / Thank you's sent | 2022-12-25 | -1

## Training
Year Round Responsibilities
Increase the number of leaders who are trained | Year End
Establish training objectives to train leaders, not just run training courses | Ongoing
Ensure Training Records are accurate | Ongoing
Promote Council Training including NYLT, Wood Badge, etc. | Ongoing
Assist the membership committee in training new adult leaders when a new unit is started | Ongoing
Help train the District Committee & Commissioner Staff | Ongoing
Spring Outdoor Leader Training (Baloo, IOLS) | 2023-03-31 | WEEKS
BEFORE
Training committee meets - Complete inventory, recruit course director, & secure location | 2022-12-09 | -16
Meeting with director - Review training outline, select instructors, review budget | 2022-12-23 | -14
Instructors Meeting - Plan program, develop promo & plan, make assignments, Order Materials | 2023-01-06 | -12
Promotion begins - unit presentations, mailers, e-mail, facebook, website | 2023-01-06 | -12
Team meets / finalize plans | 2023-03-17 | -2
Recheck all preparations, equipment, gather materials, and program gather materials | 2023-03-24 | -1
Spring Outdoor Leader Training (baloo, IOLS) | 2023-03-31 | 0
Update training inventory, follow up, budget closeout, and thank-you's mailed | 2023-04-07 | 1
Spring Leader Specific Training | 2023-03-31 | WEEKS
BEFORE
| 2022-12-09 | -16
| 2022-12-23 | -14
| 2023-01-06 | -12
| 2023-01-06 | -12
| 2023-03-17 | -2
| 2023-03-24 | -1
Spring Leader Specific Training | 2023-03-31 | 0
| 2023-04-07 | 1
Fall Outdoor Leader Training (baloo, IOLS) | 2023-10-31 | WEEKS
BEFORE
| 2023-07-11 | -16
| 2023-07-25 | -14
| 2023-08-08 | -12
| 2023-08-08 | -12
| 2023-10-17 | -2
| 2023-10-24 | -1
Fall Outdoor Leader Training (baloo, IOLS) | 2023-10-31 | 0
| 2023-11-07 | 1
Fall Leader Specific Training | 2023-10-31 | WEEKS
BEFORE
| 2023-07-11 | -16
| 2023-07-25 | -14
| 2023-08-08 | -12
| 2023-08-08 | -12
| 2023-10-17 | -2
| 2023-10-24 | -1
Fall Leader Specific Training | 2023-10-31 | 0
| 2023-11-07 | 1

## Religious
Year Round Responsibilities
Fosters and Maintains relationships with chartered partners and religious organizations | Ongoing
Works with both adults and youth in achieving their religious awards (Duty to God, Ad Adtare Dei, etc.) | Ongoing
Promotes and supports units in their Duty to God programs | Ongoing
Provides vespers services and prayers and District functions | Ongoing

## Communications
Year Round Responsibilities
Responsible for District Communicatiosn and marketing that may include website, newsletters, and social media | Ongoing
Ensure volunteers and units follow the BSA Brand Marketing Guide | Ongoing
Collects Scouting Stories that highlight local youth and the impact Scouting is having in the community | Ongoing
Works with local media to submit "good news" stories that highlight Scouting and Scouting's impact in the communit | Ongoing

## Commissioners
Year Round Responsibilities
Strive to ensure every member of the BSA has a great Scouting Experience | Ongoing
Help ensure that each unit has strong leadership and a program that attracts and retains Scouts and families | Ongoing
Identify individuals who could be asked to serve as a member of the District Committee or Commissioner Corps | Ongoing
Ensure that at least 1 Detailed Assesment is completed with every unit in the District Annually (preferably twice) | Year End
Ensure all units re-charter on time | Year End
Rescue dropped and separated Scouting units and strive to ensure that all units are active, supported, and operating | Ongoing
Work to ensure all Units complete and submit Journey to Excellence and strive for 100% gold units | Year End
Organize and provide Roundtable meetings which include breakout sessions | Ongoing
Recharter | 2023-12-16 | WEEKS
BEFORE
District Re-charter Calendar created and advertized in the May Program Planning Roundtable | 2023-05-20 | -30
Training held for Unit Commissioners and Unit Leaders on how to complete recharter with best practices | 2023-08-19 | -17
Unit Commissioners meet with, train, and support their assigned units and help them complete the re-charter | 2023-09-30 | -11
Online Re-charter Window Opens | 2023-09-30 | -11
Commissioner meet with assigned units and help them | 2023-11-11 | -5
All Unit Recharters are submitted online | 2023-12-16 | 0
Commissioners follow up with any unit who's recharter is not 100% correct and ready to post | 2023-12-23 | 1
All Unit Contacts made by commissioners during the recharter process are logged in commissioner tools | 2023-12-30 | 2
All Units are rechartered, dropped with red sheet or catagorized as a Seperated Unit | 2024-01-06 | 3